## Arbeitsmatrix
Issue Nr | Projektphase | Prefix | Issue Bezeichner | Beschreibung | Bearbeitet am | Fertigzustellen bis | Stunden Seminar | Stunden Projekt | Beginn | Ende | Mögliche Prefixe
8 | Domaenenanalyse | [TASK] | Architekturstile Recherche | Moegliche Technologien | 2021-04-07 | 2021-05-01 |  | 6
1 | Projektplanung | [TASK] | Projektplan | Erste Schaetzung und Recherche | 2021-04-06 | 2021-04-12 |  | 6 |  |  | [BUGFIX] | Fixes something that was really wrong and breaked stuff
1 | Projektplanung | [FEATURE] | Projektplan | Anlegen von OpenProject | 2021-04-09 | 2021-04-12 |  | 3 |  |  | [FEATURE] | Everything new
1 | Projektplanung | [TASK] | Projektplan | Anpassungen von OpenProject | 2021-04-10 | 2021-04-12 |  | 1 |  |  | [TASK] | Everything that has already been set up but had to be done again
1 | Projektplanung | [TASK] | Projektplan | Repository Update | 2021-04-10 | 2021-04-12 |  | 1 |  |  | [SEMINAR] | Everything done for the seminars
1 | Projektplanung | [FEATURE] | Projektplan | Issues anlegen | 2021-04-12 | 2021-04-12 |  | 0.25
4 | Domaenenanalyse | [FEATURE] | Abhaengigkeiten | Nutzeranforderungen ermitteln | 2021-04-12 | 2021-05-01 |  | 0.5
10 | User Story Mapping | [TASK] | User Stories (mapping) | Mitschrift vom Buch | 2021-04-12 | 2021-05-01 |  | 1.5
4 | Domaenenanalyse | [FEATURE] | Abhaengigkeiten | Nutzeranforderungen ermitteln | 2021-04-12 | 2021-05-01 |  | 1 | 16:25 | 17:20
1 | Projektplanung | [TASK] | Projektplan | Excel Formular | 2021-04-12 | 2021-05-01 |  | 0.5 | 17:30 | 17:45
11 | Domaenenanalyse | [SEMINAR] | Kick-Off | Zoom Call | 2021-04-13 | 2021-04-13 | 1.5 |  | 10:00 | 11:22
11 | Domaenenanalyse | [SEMINAR] | Kick-Off | Zusammenfassung | 2021-04-13 | 2021-04-13 | 2.25 |  | 12:00 | 14:15
4 | Domaenenanalyse | [TASK] | Abhaengigkeiten | Zitate gepflegt | 2021-04-13 | 2021-05-01 |  | 0.25 | 14:20 | 14:30
4 | Domaenenanalyse | [TASK] | Abhaengigkeiten | Weitere Nutzeranforderungen | 2021-04-13 | 2021-05-01 |  | 1 | 16:35 | 17:27
4 | Domaenenanalyse | [TASK] | Abhaengigkeiten | Abhaengigkeiten | 2021-04-13 | 2021-05-01 |  | 0.75 | 18:05 | 18:40
10 | User Story Mapping | [TASK] | User Stories (mapping) | Mitschrift vom Buch | 2021-04-13 | 2021-05-01 |  | 0.75 | 19:05 | 19:45
10 | User Story Mapping | [TASK] | User Stories (mapping) | Domainen Experten rekrutieren | 2021-04-14 | 2021-05-01 |  | 0.75
10 | User Story Mapping | [TASK] | User Stories (mapping) | Mitschrift vom Buch | 2021-04-16 | 2021-05-01 |  | 2 | 13:00 | 15:00
8 | Domaenenanalyse | [TASK] | Architekturstile Recherche | Uber Architektur recherchieren | 2021-04-16 | 2021-05-01 |  | 0.5
8 | Domaenenanalyse | [TASK] | Architekturstile Recherche | Architekturstile vergleichen | 2021-04-16 | 2021-05-01 |  | 1 | 18:00 | 19:00
8 | Domaenenanalyse | [TASK] | Architekturstile Recherche | Moegliche Technologien | 2021-04-19 | 2021-05-01 |  | 2 | 9:00 | 11:00
8 | Domaenenanalyse | [TASK] | Architekturstile Recherche | Architektur modellieren & planen | 2021-04-19 | 2021-05-01 |  | 1.5 | 13:00 | 14:27
12 | Domaenenanalyse | [SEMINAR] | Wissenschaftliches Arbeiten | Mind Map und Notizen | 2021-04-20 | 2021-05-01 | 4 |  | 10:00 | 14:00
13 | Domaenenanalyse | [SEMINAR] | Themenfeldanalyse | Themenfeldanalyse | 2021-04-20 | 2021-05-01 | 1.25 |  | 14:00 | 15:15
10 | User Story Mapping | [TASK] | User Stories (mapping) | Domainen Experten rekrutieren | 2021-04-23 | 2021-05-01 |  | 3 | 9:00 | 12:00
10 | User Story Mapping | [TASK] | User Stories (mapping) | Moderation und Miro board vorbereiten | 2021-04-23 | 2021-05-01 |  | 2 | 16:00 | 18:00
| Stunden insgesamt | 45.25 | Stunden Seminar | 9 | Stunden Projekt | 36.25

## Projektplan rechnung
KW | Projekt | Seminar | Selbststudium | Summe
15 | 8 | 4 | 8 | 36 | D | 107 | 2021-04-12
16 | 8 | 4 | 8 | 36
17 | 8 | 3 | 8 | 35
18 | 8 |  | 8 | 32 | K | 102 | 2021-05-03
19 | 8 | 3 | 8 | 35
20 | 8 | 3 | 8 | 35
21 | 8 |  | 8 | 32 | I | 101 | 2021-05-24
22 | 8 |  | 8 | 32
23 | 8 | 5 | 8 | 37
24 | 8 | 5 | 8 | 37 | P | 74 | 2021-06-14
25 | 8 | 5 | 8 | 37
26 | 8 |  | 8 | 32 | F | 64 | 2021-06-28
27 | 8 |  | 8 | 32
28 |  |  |  | 0
| 312 |  |  | 448 |  | 448